## Ark1
GANTT CHART - SCIENCE MUSEUM
| TASK NAME | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
|  | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Plan
Project planning | bar: WEEK 1 M; WEEK 4 M
Research | bar: WEEK 1 T to WEEK 1 W; WEEK 4 M
Sitemap | bar: WEEK 1 W to WEEK 1 Th; WEEK 4 M
Wireframing | bar: WEEK 1 Th to WEEK 2 F; WEEK 4 M
Design
Visual elements | bar: WEEK 4 M
Style tile | bar: WEEK 4 M
Possible extra illustrations | bar: WEEK 4 M
Build
HTML | bar: WEEK 2 M to WEEK 3 T; WEEK 4 M
CSS | bar: WEEK 3 T to WEEK 3 Th; WEEK 4 M
Cross-platform and cross- browser testing | bar: WEEK 3 F to WEEK 4 M
Bug fixing | bar: WEEK 4 M
Validating | bar: WEEK 4 M
Launch
Final refinements | bar: WEEK 4 M to WEEK 4 T
Report | bar: WEEK 4 M; WEEK 4 W to WEEK 4 Th
Submission | bar: WEEK 4 M; WEEK 4 F